## Sheet1
Claims Management System Corrective Action Plan March 2023
An external audit of the workers compensation Claims Management System was conducted by BRM Risk Management from 9-14 January 2023. The following corrective action plan details actions to be undertaken in response to the four observations identified.
Observations
Observation | Corrective Action | Action Officer | Date to be Completed | Status | Evidence
Element 2. Planning
Criterion 2.1 The determining authority identifies the administrative and financial limitations for each level of claims manager.
Determintations must be signed by persons and positions with delegated authority. The Delegation Schedule provides delegation of powers to the position. | All template letters were updated in 2022 to include the title 'Claims Manager', as per the Delegation Schedule. Discuss process at next fortnightly Claims team meeting to ensure old templates are archived and no longer used. | Lisa McLoughlin | 2023-03-14 | Completed | Attachment A - Team meeting invite
| Create a new Email Template for use by Claims Managers arranging reimbursement of rehabilitation expenses to employees (such as travel to and from work) that have been determined by the Rehabilitation delegate under s37. | Lisa McLoughlin | 2023-03-15 | Completed | Attachment B - Text for Email Template
Element 3. Implementation
Criterion 3.6 The determining authority complies with the provisions of the SRC Act when using its powers or meeting statutory obligations.
When arranging independent medical examinations under section 57 of the SRC Act, formal notification must be sent to the employee. | Discuss process at next fortnightly Claims team meeting to ensure all claims staff are aware of correct process and template letter to be used when advising a claimant of s57 examination. | Lisa McLoughlin | 2023-03-14 | Completed | Attachment A - Team meeting invite
| Continue to monitor use of correct templates through the annual internal audit of claims files. | Lisa McLoughlin | Ongoing | Completed | Attachment C - Auditing Process - Claims Manual
Criterion 3.14 Claim reviews are timely, made accurately and guided by equity, good conscience and the substantial merits of each case without regards to technicalities.
Documented outcomes of the ANU claims review process are not always saved in the Figtree claim file. | Discuss process at next fortnightly Claims team meeting to ensure all claims staff are aware of correct process with regard to documenting file review discussions. | Lisa McLoughlin | 2023-03-14 | Completed | Attachment A - Team meeting invite
| Develop File Review template for capturing discussions between Claims Manager and RCM regarding progress of return to work/rehabilitation programs. | Lisa McLoughlin | 2023-03-08 | Completed | Attachment D - File Review - Incapacity Claim
Element 4. Measurement and Evaluation
Criterion 4.2 The determining authority conducts an audit program - to measure performance of its claims management system.
ANU does not have a complete procedure for auditing the CMS. | Draft updates to the Claims Manual to clarify the Auditing process and procedure. | Lisa McLoughlin | 2023-03-21 | Completed | Attachment C - Auditing Process - Claims Manual